## Roadmap
Habitt v2: Feature & Fix Backlog (easiest to hardest)
RELEASE GATE: Health sync is unfinished. All rows marked 'YES' in 'Must ship before release' must be done before publishing any other changes.
Difficulty score 1-10 is an estimate based on the current code (as of 16 Oct 2026). Sources: README 'Future features', Discord notes (14.9., 23.9., 16.10.), and your extra item.
# | Feature / Task | Area | Source | What it involves | Current state in code | Difficulty (1-10) | Difficulty | Must ship before release | Status
1 | Habit-complete sound ON by default | Dopamine | Discord 14.9. | Flip the default of the completion-sound preference and make sure existing users keep their own choice. | Sound assets already exist (assets/sound/sound_01-10.mp3). | 1 | Very easy |  | To do
2 | Sleep shown as duration (e.g. 7h 30m) in habit card, not raw numbers | Health sync | Discord 14.9. | Format the sleep value in the habit card with the existing duration formatter instead of a raw number. | get_duration_string util already exists; card display needs the fix. | 1 | Very easy | YES | To do
3 | Sleep & 'wake up early' count for the day you wake up | Health sync | Discord 16.10. | Attribute a night's sleep and wake time to the wake-up day, not to yesterday's progress. | HealthService._windowFor already queries noon-to-noon for the wake-up day. Verify on device on both platforms; may already be done. | 2 | Easy | YES | To do
4 | 'Go to bed early' counts for the previous day | Health sync | Discord 16.10. | Bedtime should land on the day you went to bed (yesterday), so it needs its own window or a -1 day shift. | bedtime currently shares the sleep window, so it lands on the wake-up day. Needs a change. | 2 | Easy | YES | To do
5 | Fix: notification opens habit details on top of another habit details page | Bug | Your list | A notification tap while a details page is open should replace it, not stack a new one. | Mostly handled in commit 063d2bd (HabitRouteTracker + _navigateToHabit replaces the page). Reproduce to find any edge case that is left, e.g. a details page opened from another route. | 2 | Easy |  | To do
6 | Fix: streak wrong after completing a past day then today (amount/optional habits) | Bug | Discord 23.9. | Normal habit shows streak 2; amount/optional habit shows no streak until the habit is reopened, so the cached streak isn't refreshed after a past-day completion. | Stale streak cache in HabitStatsProvider / streak refresh path. Needs a repro and a unit test. | 3 | Easy |  | To do
7 | Confetti bursting out of the complete button | Dopamine | Discord 14.9. | Short confetti burst anchored to the button position on completion. | confetti ^0.8.0 is already in pubspec; perfect_streak_celebration.dart can serve as a reference. | 3 | Easy |  | To do
8 | Heavy sound when the full day is completed | Dopamine | Discord 14.9. | New sound asset, played once when the last habit of the day is completed (not again on undo/redo). | Needs a new audio file plus a detector for when the whole day is completed. | 3 | Easy |  | To do
9 | Daily planner: habit time ranges (README #3) | Feature | README | Bring back adjustable time ranges for habits in the new design. | README says the logic exists (e.g. Habit.getStartHour); only UI needed. | 3 | Easy |  | To do
10 | Time counter: how long you've been doing a habit + strength graph over time | Feature | README (Other) | 'Doing this for 3 months' label, plus a strength-over-time chart in habit details. | habit_strength_calculator + fl_chart already exist; need historical strength series. | 4 | Medium |  | To do
11 | Health tracking stats widget in habit details page | Health sync | Discord 14.9. | Dedicated stats card for health-linked habits (source, last sync, trends). | lib/widgets/habit_details/health_widget.dart exists. Check whether it's complete or a stub. | 4 | Medium | YES | To do
12 | Merge insight sheets into one 'all recommendations' sheet | Comeback | Discord 14.9. | Instead of several insight sheets one after another, gather them into a single sheet with all recommendations. | lib/util/insight_sheet_flow.dart currently shows sheets one at a time (debounced). Needs a refactor to collect and batch them. | 4 | Medium |  | To do
13 | Habit goals (README #1) | Feature | README | Long-term amount/duration goal; improvement sheets keep showing until the goal is reached. | Ties into insight_sheet_flow / adjust_target_dialog. New Habit field means Hive migration + backup doc update. | 5 | Medium |  | To do
14 | Workouts: investigate why there are so many workouts | Health sync | Discord 14.9. | Likely duplicate/overlapping sessions from several sources (watch + phone + 3rd-party apps) or EXERCISE_TIME vs WORKOUT mixing. | workouts read WORKOUT on one platform and EXERCISE_TIME on the other. Needs dedup by source/time overlap and testing on real devices. | 5 | Medium | YES | To do
15 | Quick break: returning after more than 3 days | Comeback | Discord 14.9. | Gentle 'welcome back' flow that makes it easy to get going again (e.g. don't punish streaks, quick catch-up). | lastOpenedDate is already tracked in util/update_last_date.dart. | 5 | Medium |  | To do
16 | Premade habit benefits (README #5) | Feature | README | Custom UI per premade habit (e.g. glasses for Drink water) and user-made quick-add presets (+10, +50, +10m, +1h). | premade_habit_catalog exists. Presets need a new Habit field and UI. | 5 | Medium |  | To do
17 | More notification personalization (README #4) | Feature | README | Notifications based on day-period completion progress, richer premade-habit texts, 5 languages. | habit_notification_text_builder + notification_text/ exist. Mostly copy + logic, needs translations. | 5 | Medium |  | To do
18 | Fresh start: returning after more than 7 days | Comeback | Discord 14.9. | 'Start fresh' dialog: pick habits to keep, pause the rest. | Habit.isPaused already exists; needs a multi-select dialog + bulk pause + interplay with notifications/streaks. | 6 | Hard |  | To do
19 | Onboarding questionnaire that recommends habits (README #6) | Feature | README + Discord 16.10. | Ask the user a few questions in onboarding, then suggest and add premade habits. | Onboarding pages + premade catalog exist; needs question flow, mapping rules, l10n in 5 languages. | 6 | Hard |  | To do
20 | Show habit next day if missed (README #2) | Feature | README | Toggle for weekly/monthly/custom habits: if missed, keep showing it daily until the next scheduled day. | Touches scheduling, 'is due today', streak/strength math and notifications. Easy to break stats, so needs tests. | 7 | Hard |  | To do
21 | Finish Apple Health & Health Connect integration overall (README #0) | Health sync | README + Discord 14.9. | Umbrella item: everything above marked 'Health sync', plus permission flows, edge cases and real-device QA on both platforms, store review requirements (privacy strings, Health Connect declaration). | Large amount already built (HealthService, HealthProvider, docs/health_sync.md). Remaining work is the sub-items and QA. | 7 | Hard | YES | To do
22 | Urgent habits (e.g. medicine) get an alarm option | Feature | README (Other) | Alarm-style notification that keeps ringing until dismissed. | Android: full-screen intent / alarm permission (USE_EXACT_ALARM policy). iOS: critical alerts need a special Apple entitlement and may not be granted. | 7 | Hard |  | To do
23 | Home screen widgets | Platform | README + Discord 16.10. | iOS WidgetKit (Swift) + Android App Widgets, showing today's habits and maybe allowing completion. | No native widget code yet. Needs home_widget or native code, App Group / shared storage (Hive is not readable by native), interactive widgets for completion. | 8 | Very hard |  | To do
24 | End-of-day Live Activity like Duolingo | Platform | README + Discord 16.10. | Before habits reset, show progress live (iOS Live Activity / Dynamic Island, Android ongoing notification) so you fill your progress in. | iOS ActivityKit needs native Swift widget extension + scheduling without a server (local start only); Android equivalent via ongoing notification. Builds on the widget setup. | 9 | Very hard |  | To do
25 | MCP server for users with an account | Platform | Discord 16.10. | Let AI assistants read/update a user's habits via MCP. | Biggest item, and it clashes with the architecture: data is local-only and backups are client-side encrypted, so a server can't read habits. Needs a backend, auth, a sync model, and a privacy-policy change. Needs a design decision before any work. | 10 | Very hard |  | To do

## Summary
Summary
Difficulty | Tasks | Done
Very easy | 2 | 0
Easy | 7 | 0
Medium | 8 | 0
Hard | 5 | 0
Very hard | 3 | 0
Total | 25 | 0
Release blockers (Health sync) | 6 | 0
Release unblocked? | NO - finish Health sync first
Scale: 1 = Very easy, 2-3 = Easy, 4-5 = Medium, 6-7 = Hard, 8-10 = Very hard.
Edit the Status column on the Roadmap sheet (To do / In progress / Done / Verify); this sheet updates automatically.